## Sheet1
Week No. | Task | Milestone
Week1 | Project start: Kick-off Session, get familiar with project requirements & background | No
Week2 | Analysis stage: Define project scope, design work plan & literature review about project topic | No
Week3 | Analysis stage: Data extraction, deeper literature review about suitable techiniques & sentiment analysis | No
Week4 | Analysis stage: Exploratory Data Analysis & visualization, project prosoal writing task allocation | No
Week5 | Project proposal due | Milestone 1
Week6 | Developmennt stage 1: Finish visualization & coding for prediction based on historical price | No
Week7 | Developmennt stage 1: coding for prediction based on historical price | Milestone 2
Week8 | Developmennt stage 2: Coding for prediction based on social media data | No
Week9 | Progress Report due | No
Week10 | Development stage 2: Coding for prediction based on social media data | Milestone 3
Week11 | Testing stage: test for model performance | No
Week12 | Ending stage: Final report writing & prepare for presentation | No
Week13 | Final report due | Milestone 4